## Sprint 1
|  | Date | Stories Moved to Done
Date | Remaining Points | 2018-02-08 | (0.5) As a developer, I want the application to open the search page (home screen) whenever it is first opened so that the user has a consistent home screen. [1]
2018-02-02 | 39.5
2018-02-05 | 39.5
2018-02-06 | 39.5
2018-02-07 | 39.5 | 2018-02-09 | (3) As a user, I want to view a help page so that I know how to use the application. [5]
2018-02-08 | 39
2018-02-09 | 34 |  | (2) As a user, I want to open the settings page with a button so that I can view the settings page. [3]
2018-02-12 | 32
2018-02-13 | 30
2018-02-14 | 30 | 2018-02-12 | (2) As a developer, I want a splash screen that is shown while the search page (home screen) loads so that the user knows the application is loading. [2]
2018-02-15 | 27
2018-02-16 | 4
Velocity | 35.5 | 2018-02-13 | (2) As a user, I want to open the help page with a button that is located on every page so that I can view the help page. [5]
|  | 2018-02-15 | (3) As a user, I want to view a settings page so that I can change the settings in the application. [5]
|  | 2018-02-16 | (2) As a user, I want to have a back button on each page so that I can return to the previous page. [2]
(3) As a developer, I want each page to have a basic design so that I can move from page to page. [2]
(1) As a user, I want to be able to click the banner from every page so that I can always return to the search page. [3]
(2) As a developer, I want to a search by state so information is returned about the species. [5]
(2) As a developer, I want to a search by county so information is returned about the species. [8]
(13) As a developer, I want to pull relevant info from the APIs, based on the scientific name, so that I have a way to display the data consistently. [21]

## Sprint 2
Date | Stories Moved to Done |  |  | Date | Remaining Points
2018-03-08 | (8) As a user, I want to be able to choose what I am searching by so that I can switch what I am searching for. [8] |  |  | 2018-02-19 | 52
|  |  |  | 2018-02-20 | 52
2018-03-10 | (3) As a developer, I want to search by scientific name so information is returned about the species. [2] |  |  | 2018-02-21 | 52
| (3) As a developer, I want to search by common name so information is returned about the species. [8] |  |  | 2018-02-22 | 52
|  |  |  | 2018-02-23 | 52
2018-03-11 | (5) As a developer, I want to create 15 tests so that I can have a routine way of checking and improving the application's functionality. [5] |  |  | 2018-02-26 | 65
| (3) As a developer, I want to create a "What's Around Me?" button so that I can view the species in a set geographic area. [3] |  |  | 2018-02-27 | 65
| (3) As a user, I want the results to be selectable so that I can move to the species page for that entry. [2] |  |  | 2018-02-28 | 65
| (5) As a developer, I want to create a consistent design and color scheme laid out in a style document so it can be referenced when creating and adding to pages. |  |  | 2018-03-01 | 65
| (3) As a developer I want to make all of the pages conform to the style document. |  | BREAK | 2018-03-02 | 70
| (5) As a developer, I want to improve search by county so that... [8] |  |  | 2018-03-05 | 70
| (5) As a user, I want to load more results by scrolling to the bottom of the screen and selecting a "Load more" button so that I can view more results. [8] |  |  | 2018-03-06 | 70
| (13) As a developer, I want a layout of all the pages of our application so that we have a starting point when we begin designing these pages. [8] |  |  | 2018-03-07 | 70
| (1) As a user, I want to move to a species page when I select a species from the list so that I can view more information about it. [0] |  |  | 2018-03-08 | 62
| (5) As a developer, I want the species page to be populated with information about the species so that the user can learn more about that species. [5] |  |  | 2018-03-09 | 62
|  |  |  | 2018-03-10 | 56
|  |  |  | 2018-03-11 | 8
|  |  |  | Velocity | 62
|  | started with | 52
|  | 2018-02-25 | 13
|  | 2018-03-02 | 5

## Sprint 3
Date | Stories Moved to Done | Points | Date | Remaining Points | Ideal
2018-03-15 | (3) Create the layout of the map page and allow the user to be redirected to the map page. | 3 | 2018-03-12 | 79 | 73.1786 | ideal slope = | 5.8214
2018-03-16 | (8) As a user, I want the application to save my search history so that I have a reference to what I previously searched. [8] | 8 | 2018-03-13 | 79 | 67.3571
2018-03-17 | (2) As a developer, I want to update the help page so that it includes the newest application information. | 2 | 2018-03-14 | 79 | 61.5357
| (2) Allow the user to search by county using state abbreviations | 2 | 2018-03-15 | 76 | 55.7143
2018-03-18 | (0.5) Allow user to search by state using state abbreviations. | 0.5 | 2018-03-16 | 68 | 49.8929
2018-03-20 | (5) As a user, I want to be able to clear my search history so that the history doesn't take up space on the phone. | 5 | 2018-03-17 | 66 | 44.0714
| (8) As a developer, I want to coordinate GPS data into the application so that I can input it into the "What's Around Me?" button/request. | 8 | 2018-03-18 | 66 | 38.25
2018-03-25 | (8) As a developer, I want to improve the style and design of the application so that the application looks clean and professional. | 8 | 2018-03-19 | 66 | 32.4286
| (8) As a user, I want to be able to view an image of the species on the SpeciesInfoPage so that I can see examples of the species. | 8 | 2018-03-20 | 53 | 26.6071
| (5) As a developer, I want to create about 15 additional tests so that the application's new features can be tested. | 5 | 2018-03-21 | 53 | 20.7857
| (8) As a developer, I want to add an overflow menu to contain multiple icons on the action bars of the application so that the screen is not cluttered. | 8 | 2018-03-22 | 53 | 14.9643
| (8) Research how to implement the map page and begin implementing the map page. | 8 | 2018-03-23 | 53 | 9.1429
| (8) As a developer, I want to filter by some characteristic (genus) so that I can get an idea of what filtering in the application will look like. | 8 | 2018-03-24 | 53 | 3.3214
| (5) As a developer, I want to make sure the search by common or scientific name produces multiple results for the user only inputs part of a common or scientific name so that the user has all options to see and select. | 5 | 2018-03-25 | 3 | -2.5
|  |  | Velocity | 76
Storys to move
(3) As a developer, I want to fix the bug with SpeciesInfoPage that causes it to display null for all data so that it displays the information it should

## Sprint 4
Date | Stories Moved to Done | Points |  | Date | Storys to move | Points
2018-03-28 | (3) As a developer, I want to add the common name to the selectable list populated by the search by county and search by state so that I can see both the common and scientific name. | 3 |  |  | (21) As a developer, I want the user to be able to upload pictures and recordings on the Personal Recordings page. | 21
2018-03-30 | (8) Have the map zoom on the location that the user performed a sightings search on. | 8 |  |  | (8) As a developer, I want to redesign the layout of the SpeciesInfoPage so that it conforms to the style document. | 8
2018-04-02 | (2) As a developer, I want to save the user settings so that it defaults when the app is opened. | 2 |  |  | (3) As a developer, I want to only send the scientific name from the search page to the SpeciesInfoPage. | 3
2018-04-05 | (8) As a developer, I want to figure out how to translate latitude and longitude to miles so that I can use that measurement in the "What's Around Me?" functionality. | 8 |  |  |  |  | 83
2018-04-08 | (8) As a developer, I want to coordinate the "What's Around Me?" function with the most recent search so that the user can filter by their location. | 8
| (5) Improve layout of map page and make sure it conforms to the other pages. | 5
| (8) As a user, I want be able change the color of the application in the settings so that I can have multiple options color wise. | 8
| (3) As a developer, I want to have about 40 tests that pass so that the application's features can be tested. | 3
| (3) As a developer, I want to only send the scientific name from the search page to the SpeciesInfoPage. | 3
| (3) As a developer, I want to fix the bug with SpeciesInfoPage that causes it to display null for all data so that it displays the information it should | 3
|  |  | Date | Remaining Points
|  |  | 2018-03-26 | 98
|  |  | 2018-03-27 | 98
|  |  | 2018-03-28 | 95
|  |  | 2018-03-29 | 95
|  |  | 2018-03-30 | 87
|  |  | 2018-03-31 | 87
|  |  | 2018-04-01 | 87
|  |  | 2018-04-02 | 85
|  |  | 2018-04-03 | 85
|  |  | 2018-04-04 | 85
|  |  | 2018-04-05 | 77
|  |  | 2018-04-06 | 77
|  |  | 2018-04-07 | 77
|  |  | 2018-04-08 | 47
|  |  | Velocity | 51

## Sprint 5
Date | Stories Moved to Done | Points |  | Date | Storys to move | Points
2018-04-10 | (1) As a developer, I want to set a default theme when the app is launched for the first time so it doesn't crash | 1 |  |  | (21) As a developer, I want the user to be able to upload pictures and recordings on the Personal Recordings page. | 21
| (5) As a developer, I want to fix the bug where images don't display on the speciesinfoPage so the user can see them. | 5 |  |  | (8) As a developer, I want to redesign the layout of the SpeciesInfoPage so that it conforms to the style document. | 8
| (5) As a developer, I want to fix the bug with descriptions causing them to display HTML so that the description is readable. | 5 |  |  | (3) As a developer, I want to only send the scientific name from the search page to the SpeciesInfoPage. | 3
2018-04-14 | (5) As a developer, I want an additional search bar for state when the user searches by county in the search page and map page to improve the user experience. | 5 |  |  |  |  | 91
2018-04-16 | (5) Allow the user to view sightings near their GPS location on the map page. | 5
2018-04-17 | (13) As a developer, I want the user to be able to upload pictures on the Personal Recordings page. | 13
2018-04-18 | (5) As a developer, I want to add about 10 additional tests so that the application's features can be tested. | 5
2018-04-19 | (2) Cleaned up number of results and improve load more functionality. | 2
2018-04-20 | (13) As a developer, I want to be able to group pictures into directories based on animals/sightings. | 13
2018-04-21 | (5) Include better error handling in map page. | 5
| (1) Add additional error handling in search page. | 1
| (8) As a developer, I want to display the user's uploaded pictures along with a name and description. | 8
2018-04-22 | (2) Update help page to reflect all of the final features. | 2
| (8) As a developer, I want to allow a user to be able to create a directory on the personal recordings page. | 8
| (8) As a developer, I want to redesign the layout of the SpeciesInfoPage so that it conforms to the style document. | 8
| (8) As a developer, I want to clean up and reorganize the code and create methods to simplify the readability of the code. | 8
| (13) As a developer, I want to filter by kingdom so that the user can narrow their search. | 13
|  |  | Date | Remaining Points
|  |  | 2018-04-09 | 107
|  |  | 2018-04-10 | 96
|  |  | 2018-04-11 | 96
|  |  | 2018-04-12 | 96
|  |  | 2018-04-13 | 96
|  |  | 2018-04-14 | 91
|  |  | 2018-04-15 | 91
|  |  | 2018-04-16 | 86
|  |  | 2018-04-17 | 73
|  |  | 2018-04-18 | 68
|  |  | 2018-04-19 | 66
|  |  | 2018-04-20 | 53
|  |  | 2018-04-21 | 39
|  |  | 2018-04-22 | 0
|  |  | Velocity | 107